PROGRESS REPORT ON THE IMPLEMENTATION OF KFW GRANT

FUNDED BY THE FEDERAL GERMAN GOVERNMENT

# Presented by

# Moldova Social Investment Fund

# 30 June, 2015

# Chisinau – 2015

ABBREVIATIONS AND ACRONYMS

| BMZ | German Federal Ministry for Economic Cooperation and Development |
| --- | --- |
| CC | Community Contribution |
| CD | Community Development |
| DFID | Department for International Development |
| EC | Executive Committee |
| EU | European Union |
| FC | German Financial Contribution |
| IA | Implementing Agency |
| IDA | International Development Association |
| JSDF | Japan Social Development Fund |
| KfW | German government-owned development bank „Kreditanstalt fur Wiederaufbau” |
| LPA | Local Public Administration |
| MSIF | Moldova Social Investment Fund |
| OM | Operational Manual |
| SIDA | Swedish International development Agency |
| SP | Subproject |
| RM | Republic of Moldova |
| UNICEF | United Nations Children’s Fund |

# CONTENTS

| # Introduction | # 4 |
| --- | --- |
| # KfW Project implementation progress: | # 5 |
| # Capacity building | # 5 |
| # Subprojects in villages that work with MSIF for the first time (“new” communities) | # 6 |
| # Subprojects in villages and small towns that have already implemented one or more subprojects with MSIF (“repeatedly come” communities) | # 6 |
| # Partnership subprojects between communities in post-conflict region | # 7 |
| # Energy efficiency measures in public infrastructure | # 8 |
| # Brief summary | # 8 |
| # Procurement and financial activities | # 10 |
| # Best practices | # 11 |
| # Lessons learned | # 11 |
| # Challenges / risks and measures to prevent them | # 12 |
| # Annexes | # 13 |
| # Annex 1. The cycle of subproject implementation: Step by step | # 13 |
| # Annex 2. Progress of subprojects implementation (“new” communities) | # 14 |
| # Annex 3. Progress of subprojects implementation (“repeatedly come” communities) | # 16 |
| # Annex 4. Progress of subprojects implementation in post-conflict region | # 18 |
| # Annex 5. Selective Project performance results | # 19 |

# Introduction

The Moldova Social Investment Fund (MSIF) is a project created with a financial support of the World Bank and donor countries. MSIF is a juridical, independent, non-commercial and non-profit unit. Its purpose is to contribute by external funds to the implementation of the national strategies and programs through empowering local communities and their institutions in management of their primary development needs.

During its activity, MSIF has managed an amount of ~ 140 mln USD coming from the World Bank and offered by different donors (SIDA, DFID, JSDF, EU, KfW, UNICEF etc.), as those allocated from the State budget. Besides, MSIF has been also contracted by local and foreign organizations for consulting services in managing projects in the country and abroad supported by external donors.

In 2013 – 2015 MSIF has implemented infrastructure projects and programs supported by different donors, as follows:

- The Technical and Financial Assistance Program offered by the Government of Romania for preschool institutions of Republic of Moldova;

  - Infrastructure subprojects with the use of labor intensive construction methods, International Development Association;

  - Community participation in the post-conflict regions, Japan Social Development Fund Grant;

  - Promotion of sustainable development strategies in the renewable energy technologies sector through piloting of demonstration projects based on usage of solar energy and agricultural wastes, European Union Grant;

  - Global Partnership for Education Project for improving the access to quality early education for preschool age children;

  - Modeling of services for children under 3 years Program, UNICEF Grant;

  - Social Infrastructure and Energy Efficiency Project, KfW Grant:

  - Integration of Children with Disabilities into Mainstream Schools Project, PHRD Grant.

By signing a Financing and Project Agreement with respect to the extension of KfW’s Financial Contribution amounting to 5 mln Euro as a non-repayable grant, as well as local communities’ contribution – at least 0,66 mln Euro, MSIF (project-executing agency) started the implementation of “Social Infrastructure and Energy Efficiency” Project (BMZ No.: 2009 66 440).

The Project concerns investments in municipal social infrastructure (sanitary and water supply, schools, kindergartens, roads etc.) of local communities of up to 20 000 inhabitants with a specific focus on the efficient use of energy and the use of alternative energy recourses.

The purpose of the Project is the sustainable use of improved municipal services, as well as a more efficient use of energy for or by the population of the Project region (ten northern raions of Moldova and post-conflict region). This is to contribute to improved social living conditions for the population as well as its income situation, an improved situation of the environment and to the development of good local governance.

The above mentioned purpose corresponds to the purpose specified in the Financing and Project Agreement.

Project activities are the following:

- Implementation of subprojects of community development:

- Subprojects in villages that work with MSIF for the first time (“new” communities),

- Subprojects in villages and small towns that have already implemented one or more subprojects with MSIF (“repeatedly come” communities),

- Partnership subprojects, as above, between communities in post-conflict region.

- Energy efficiency measures in public infrastructure.

The maximum financial size for subprojects in villages amounts up to 100,000 USD (75,000 USD in villages that work with MSIF for the first time), up to 150,000 USD in towns of up to 10,000 inhabitants and up to 200,000 USD in towns of up to 20,000 inhabitants. A minimum community contribution of 15% of the subproject costs is required from the beneficiary communities. In the case of villages and small towns that have already implemented one or more subprojects with MSIF is required 30%.

The structure of the planned Project budget is illustrated below (see Figure 1).

Figure 1. The structure of Project’s budget

As Project-Executing Agency, MSIF supports the beneficiary communities in preparation and implementation of subprojects, according to the procedures laid out in its Operational Manual, which forms an integral part of the Separate Agreement under KfW Grant.

# KfW Project implementation progress

Capacity building

MSIF represents a mechanism of financial resources management through Community Development approach. This approach is also applied within the implementation of KfW Grant. The beneficiary communities are encouraged to actively involve the population into community development and decision making process through:

- Identification of priority community issues (organization of focus groups, general meetings, referendums, open meetings of local councils, public audiences, etc.);

- Active community involvement in the process of subproject proposals preparation and their implementation (participative evaluation and monitoring, contribution collection, procurement of design and construction companies’ services, etc.);

- Creation on a voluntary basis of subprojects’ implementing agencies and community sustainability funds;

- Continuous training and technical assistance for initiative community groups (implementation agencies, beneficiaries’ associations, local public administration representatives) at subprojects implementation and post-implementation stages;

- Ensuring the sustainability of investments/the objectives renewed with MSIF support;

- Development of the community ownership sense and responsibility of the community members for their future, etc.

The whole cycle of subproject implementation by MSIF is totally based on citizen participation approach (see Annex 1). In this context it is to mention that during Grant’s implementation there have been trained ~ 2020 persons, while in the process of community primary needs identification there have been included up to 50 % of communities’ adult population through:

- over 516 focus groups with more than 7080 participants,

- over 98 community general/representatives’ meetings with more than 33320 participants, inclusive ~ 20580 women,

- 19 referendums with ~ 28360 residents involved,

- 17 open sessions of town councils.

Subprojects in villages that work with MSIF for the first time (“new” communities)

Basing on Amendment 1 to the Separate Agreement, during the first year of Project implementation the access to the German financial contribution was open for northern rural communities, which haven’t implemented any subprojects with MSIF’s support before.

The concerned communities,  the majority of which are small with underdeveloped infrastructure, situated far from raion centres, expressed interest to participate in the Project and identified their priority needs (renovation of schools and kindergartens, re/construction of local roads, rehabilitation/construction of sewerage and water supply systems, etc.)

Local public administrations together with Implementing Agencies set up at community general meetings developed subproject proposals and submitted them to MSIF. The proposals included the volumes of works necessary to be executed, including: reconstruction of roof, replacement of windows and doors, renovation of heating and electricity systems, thermal insulation of the building, provision with drinkable water public facilities and private households, mounting water towers, arrangement of sidewalks, etc.

Subprojects implementation is mostly determined by communities’ involvement and activism due to the principle “First come – first served” (referring to development of technical design and collection of local contribution). The “new” beneficiary communities contributed to the implementation of their subprojects with minimum 15 % of their costs. The estimated community contribution (“new” communities) is about 288299 Euro.

In total, 33 subprojects identified by the “new” communities from the North of Moldova have been supported under the Project, including 1 subproject at the bidding stage in the report period. The progress of subprojects implementation (“new” communities) is registered in Annex 2.

Subprojects in villages and small towns that have already implemented one or more subprojects with MSIF (“repeatedly come” communities)

Following the Agreement, in October 2012 the access to the German Financial Contribution was open to the communities from the northern part of Moldova that have already implemented one or more subprojects with the MSIF.

Though it is easier to attract and organize the experienced and active communities, which have already gained benefits and taste in solving community problems through implementing projects with external financial support, the speed of implementing subprojects in “repeatedly come” communities is not so high. One of the main reasons is the necessity to collect at least 30 % of local contribution for subproject implementation that requires 4-6 months.

Still these communities are both interested and experienced in raising additional funds in order to assure their community development. The estimated community contribution (“repeatedly come” communities) is about 648011 Euro.

In total, 29 subprojects identified  by the “repeatedly come” communities from the North of Moldova have been supported under the Project, including 4 subprojects finished and 1 subproject under implementation in the report period. The progress of subprojects implementation (“repeatedly come” communities) is registered in Annex 3.

Partnership subprojects between communities in post-conflict region

With the support of KfW Grant MSIF continues its activity of establishing partnership and confidence building between the communities in post-conflict region through the implementation of social infrastructure/community development subprojects.

Due to the specific “status” of the post-conflict region, the process of subprojects implementation has required more time, discreetness and care. The region remains to be a closed space, with lack of the necessary legal field for investments, etc.

From the very beginning of Project’s operation MSIF started an information campaign and consultations with region’s leadership of different levels regarding the availability of an external financial support. On behalf of the region, the Commission of Humanitarian and Technical Aid has been mostly involved in the process of negotiation and preparation of Grant’s arrival to Transnistrian communities. In order to facilitate the process of Grant implementation, there was employed a community development consultant from the region. Meanwhile there were identified the best options of Grant implementation, as well as examined the eventual risks of the implementation process. The launch of KfW Grant in Transnistrian region was preliminary assigned and then postponed for several times.

It is worth mentioning that the separatist authorities continue to challenge MSIF’s procedures at every stage of subprojects implementation that definitely delays the rhythm of subprojects implementation: the opportunity of a community to benefit by external funds is determined by the Transnistrian Commission on Humanitarian and Technical Aid in an exceptional way that requires time; the separatist authorities tend to condition the activity of the construction companies contracted to execute civil works, especially those from the right side of Nistru, continuously addressing more and more new requirements to the contractors regarding the legalization of their activity in the region (registration, license, transportation of building materials, etc. – that leads to more expenditures for the contractors and enforce them to withdraw from the contracts), etc. Nevertheless, MSIF continues to work, step by step, on the implementation of the Project in the post-conflict region.

The estimated community contribution (in post-conflict region) is about 199345 Euro.

In total, 27 subprojects identified by the communities from the post-conflict region have been supported under the Project, including 9 subprojects finished, 2 subprojects under implementation, 1 subproject at the bidding stage in the report period. The progress of subprojects implementation in post-conflict region is registered in Annex 4.

# Energy efficiency measures in public infrastructure

The modalities of implementation and scope of measures to improve energy efficiency were prepared with assistance of an expert mission. Friedrichsdorfer Institut zur Nachhaltigkeit (IzN) from Germany was involved in planning Project activities, having supported MSIF through a theoretical support (trainings) and site visits in Moldova, as well as the organization of a study visit of MSIF’s staff to Germany.

The participants of the study tour learned and drew from lessons, experiences and good practices of Germany’s energy efficiency and alternative energy production technologies and their application, particularly bio-fuel production and Passive House technology. Consequently, MSIF applies some elements of energy efficient technologies through its whole activity of implementing repair works at schools, kindergartens, social and health care services centers from the Republic of Moldova, irrespective of the financial sources.

Basing on the comprehensive analyses: modern technology and developed countries’ experience in the field, the available budget, local background, including the capacity and availability of human resources and construction materials etc., it was decided to pilot construction of an energy efficient kindergarten for 100 children. The kindergarten shall be built in Calarasi town which needs to include a greater number of preschool kinds into the educational process. Calarasi is situated in the center of the country that shall allow promoting of the new applied technologies.

A local design company “Axis Mundy” Ltd was contracted to develop the appropriate technical design with an essential assistance of Rongen Architekten GmbH. The relevant technical design was developed and the necessary approval of the State Services for verification and expertise of designs and constructions was obtained in the report period. The execution of construction works will begin in the second half of 2015.

Brief summary

It is important to note the synergy between different financial sources managed by MSIF. Thus KfW’s Financial Contribution was complimented with about 125900 Euro from the Technical and Financial Assistance Program offered by the Government of Romania for preschool institutions of Republic of Moldova (see Annex 5).

In total, to date under KfW Grant there are 89 subprojects approved for funding, including 84 sp fully completed (13 subprojects completed in the report period), 3 subprojects under implementation and 2 subprojects at the bidding stage. The community contribution collected up to the report period is about 1,025 mln Euro, which exceeds Financing and Project Agreement provisions about 0,66 mln Euro local communities’ contribution (selective Project performance results see in Annex 6). The typology of subprojects is illustrated in the Table below.

Subprojects by typology:

| Renovation works at schools and kindergartens | 57 |
| --- | --- |
| Renovation works of water supply | 13 |
| Renovation works of roads | 11 |
| Renovation works at hospitals | 3 |
| Renovation of street lighting (EE) | 3 |
| Renovation works at community youth centre | 1 |
| Renovation works at community centre for elders | 1 |

As a result of infrastructure subprojects implementation the following achievements have been registered to date:

- Renovation of educational facilities (schools, kindergartens, educational complexes):

- 20576 m2  of roof reconstructed,

- 8785 m2 of windows and doors replaced,

- 7463 m2 of floors repaired,

- 27278 m2 of walls and ceilings renovated,

- 4 boiler rooms with 6 boilers (solid fuel - biomass) arranged,

- 6 heating networks installed,

- 8275 m2 of façade insulated,

- 51 sanitary blocks (inclusive provision of water and sewage) rehabilitated.

- Renovation / construction of water and sewerage systems:

- 64783 m of water conduits constructed,

- 12 water reservoirs mounted,

- 10 artesian wells rehabilitated,

- 13 protection areas of water sources arranged.

- Re/construction of local roads and paving sidewalks:

- 29466 m2 of local roads/sidewalks renovated,

- 17645 m of kerbstones installed.

- Heating water (solar collectors):

- 32 panels of solar collectors (each of 30 vacuum tubes) and 10 storage tanks mounted.

- Street lighting network:

- 16800 m of electrical networks on new and existing pillars installed,

- 316 LED installed.

It worth mentioning, that within the subprojects of social facilities under KfW Grant MSIF has applied different elements of energy efficiency (thermal insulation, biomass boilers for space heating, solar collectors for water heating etc.).

Over 2178 temporary workplaces, were created during the subprojects implementation with duration of 2 - 8 months each.

Over 62586 people in the beneficiary communities, including 16120 people in the report period, gained a better access to quality and improved infrastructure services. The beneficiaries assure sustainability of the rehabilitated facilities according to the appropriately developed action plans.

Procurement and financial activities

In accordance with the Financing and Project Agreement, all the contracts for works, goods and services financed from the KfW Grant are awarded pursuant to the regulations for procurement described in the MSIF’s Operational Manual.

The procurement activity within MSIF is based on organizing the procurement of works, goods and services as well as on monitoring the purchases made by the investments beneficiary communities, the main objective being a high degree of efficiency, transparency and savings.

All the procurement related to the subprojects (selection of design company, construction company and technical supervisor) are decentralized and the responsibility to conduct the tenders is delegated to the communities. A Tender Evaluation Commission has been created at community level, the members of the commission being the representatives of local public administration and Implementing Agencies.

MSIF procurement team assists and trains the beneficiary communities at each procurement stage: (i) selection of the design company; (ii) publication of announcements; (iii) preparation of tender documents; (iv) evaluation of tender results; (v) negotiation of the contract. A total number of 250 persons attended the trainings regarding the selection of the design company, construction company and technical supervisor.

MSIF provided technical assistance to 97 communities in publishing the announcements in the Official Gazette (Monitorul official), local mass media and MSIF’s website.

A total number of 90 tenders were organized to employ construction firms and 33 tenders to select local supervisors. All the tenders were valid and resulted in 92 civil works contracts and 31 contracts signed with the local supervisors selected by communities.

A total number of 449 bidders participated in the tenders organized for selecting the construction company (on average 5 bidders per tender).

No serious problems were encountered in the process of tender organization, communities respecting in general the procurement rules provided in the Operational Manual. No complaints were registered from tender participants within the period of the report.

To date MSIF disbursed EUR  3.180.126,85 from the FC funds.

The community contribution collected by now is 1,025 mln Euro that overcomes the expected value of at least 0,66 mln Euro  according p.3 Total Cost and Financing from Separate Agreement to the Financing and Project Agreement.

The financial statements of the KfW Grant have been audited by an independent auditor – Sos-Audit Ltd (Armenia), selected on competitive basis from World Bank’s list of eligible auditors. The independent auditor’s reports were presented to KfW for each fiscal year.

Best practices

During the implementation of KfW Grant, MSIF has accumulated an imposing experience and managed to promote a range of good practices which are replicated by different governmental institutions and nongovernmental organizations in the relevant fields.

The main of them are the following:

- Identification of community priority needs and problems by the population;

- Participatory identification of different resources, including funds necessary for community needs;

- Involvement of population and local actors into the decision making process, strengthening efforts and funds, monitoring and evaluation etc. regarding community problems solving;

- Management/administration of local and external funds;

- Development of intra/inter partnerships by the communities;

- Community meetings;

- Development of the associative sector, support in establishment and development of public associations and their activities;

- Piloting new construction materials and technologies;

- Modification of the standards in the fields of construction, education and energy;

- Piloting alternative energy resources.

Lessons learned

- Trainings conducted in cooperation: foreign experts – local experts have a great impact on the efficiency of introduction new energy efficiency technologies under MSIF Project. Thus, local experts study work methods practiced by international experts that contribute to the development of capabilities and new employment perspectives in the future.

- The implementation of innovative technologies requires an intensive collaboration with relevant ministries, organizations and institutions to coordinate activities, sustain a constant exchange of information and learned lessons, as well as adoption of positive experiences. The combined effort of various organizations (financial, human resources, etc) in implementing projects leads to the development of new, innovative and efficient technologies with an important impact on the communities.

- Participative involvement enhances the objectivity in evaluating the sustainability of subprojects implemented with MSIF support.

- The evaluation of the current state of the facilities renovated with MSIF assistance contributes to an increased sense of community ownership and responsibility of the local agents and residents for their maintenance and expansion.

- Community contribution (funds donated by local residents and local public authorities, economic agents, etc.) is an efficient mechanism of assuring sustainability of the rehabilitated objects/facilities.

- The involvement of community agents/local residents in MSIF investment impact evaluation contributes to the development of capabilities in evaluating local-level actions and encourages communities to be proactive.

- The implementation of subprojects with a high degree of transparency with the major involvement of population in managing local and external financial means and delegating various functions to communities facilitates and ensures a sustainable community development.

- Consolidation of community agents and local residents’ efforts in solving priority community problems, solicited by MSIF procedures, was confirmed to be an efficient mechanism to ensure community development even in times of economic, social and political crisis.

Challenges / risks and measures to prevent them

    - Instable situation in the post-conflict region, which can also affect the rhythm of civil works execution by the construction companies selected/hired on the basis of the tenders, organized in compliance with MSIF’s procedures.

MSIF will continue applying the approach of permanent negotiation and discussions regarding each step/stage of subprojects implementation in order to assure a full compliance with Operational Manual provisions.

    - Local construction companies have little experience in the field of Passive House technologies.

Before starting construction works execution, the winner company will benefit by a special training in quality assurance provided by the German experts also involved into designing now. The experts will periodically monitor the process of construction too.

    - The available budget for the implementation of the pilot subproject regarding the construction of an energy-efficient kindergarten can be insufficient.

In case it is established that the funds reserved for the pilot subproject are insufficient, the necessary additional amount will be covered from the other expenditure items of the Project.

    - The high estimated cost of the pilot subproject on energy efficiency can require more time for implementation/civil works execution. Along with the first challenge from the list (instable situation in the post-conflict region), it can cause a delay in the completion of the Financing and Project Agreement in time.

Based on the progress of subprojects implementation, when required, MSIF will preliminarily initiate the procedure of extension of the Agreement term.

# Annexes

Annex 1. The Cycle of Subproject Implementation: Step by Step

Step 1. Launching the German Grant

Publishing announcements in governmental edition and MSIF’s website, meeting with raions’ leadership.

Step 2. Promotion, identification and development of subproject proposals

  - Promotional workshops at raion and local levels;

  - Focus-groups and community general meetings, identifying community primary problems, setting up Agencies of Subproject Implementation;

  - Development of subproject proposals and their submission to MSIF.

Step 3. Subprojects appraisal and approval

  - Assessment of SP proposals camerally and on the site with participation of local and raion authorities and citizens (social/institutional, technical and financial feasibility);

  - Development of the necessary technical documentation, identification of community contribution, development of action plans regarding assurance of investments’ sustainability;

  - Community’s justification of the identified volumes of works needed to be funded within the meetings of MSIF Executive Committee.

Step 4. Procurement

Communities follow MSIF procedures when purchasing services of construction company and technical supervision, while MSIF releases its No-Objection.

Step 5. Civil works, guarantee period and handover of the object

  - Monitoring the quality of works, building materials, validity of guarantee certificates;

  - Processing payments by MSIF to contractors referring to the volumes of work accepted by the community;

  - Removal of eventual shortcomings.

Step 6. Post implementation and subprojects sustainability

According to the action plans developed by Subproject Implementing Agencies and approved by the Local Councils.

The beneficiary communities are supported by MSIF at each stage through appropriate trainings, informational consulting and technical assistance.

## Annex 2. Progress of subprojects implementation (“new” communities)

| # | Community | SP | Estimated budget (EUR) | Estimated KfW FC (EUR) | Disbursed KfW (EUR) | Estimated CC (EUR) | Stage |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Balasinesti (r. Briceni) | Repair works in gymnasium | 59 522 | 50 594 | 40902 | 8 928 | F i n i s h e d F i n i s h e d F i n i s h e d F i n i s h e d F i n i s h e d F i n i s h e d F i n i s h e d F i n i s h e d |
| 2 | Birnova, (r. Ocnita) | Repair works in kindergarten and gymnasium | 58 998 | 50 148 | 47506 | 8 850 |  |
| 3 | Bobulesti (r. Floresti) | Repair works in kindergarten | 47 479 | 40 357 | 27625 | 7 122 |  |
| 4 | Bulboaca (r. Briceni) | Repair works in kindergarten and gymnasium | 58 191 | 49 462 | 44984 | 8 729 |  |
| 5 | Casunca (r. Floresti) | Construction of a portion of aqueduct | 57 591 | 48 952 | 36983 | 8 639 |  |
| 6 | Dominteni (Drochia) | Repair works in gymnasium | 57 668 | 49 018 | 35450 | 8 650 |  |
| 7 | Fintina Alba (r. Edniet) | Renovation of water supply system | 60 464 | 51 394 | 23937 | 9 070 |  |
| 8 | Gordinesti (r. Edinet) | Repair works in lyceum | 55 129 | 46 860 | 34118 | 8 269 |  |
| 9 | Gvozdova (r. Floresti) | Construction of a portion of aqueduct | 41 434 | 35 220 | 15814 | 6 214 |  |
| 10 | Malaiesti (r. Riscani) | Renovation of a portion of aqueduct | 16 493 | 14 019 | 11210 | 2 474 |  |
| 11 | Marcauti (r. Briceni) | Repair works in gymnasium | 57 228 | 48 644 | 29860 | 8 584 |  |
| 12 | Mihalaseni (r. Ocnita) | Repair works in educational complex | 69 591 | 59 152 | 49980 | 10 439 |  |
| 13 | Ocolina (r. Soroca) | Repair works in kindergarten | 49 457 | 42 038 | 35243 | 7 419 |  |
| 14 | Parcova (r. Edinet) | Repair works in gymnasium | 58 112 | 49 395 | 30102 | 8 717 |  |
| 15 | Petreni (r.Drochia) | Repair works in kindergarten | 25 424 | 21 610 | 18647 | 3 814 |  |
| 16 | Pirjota (r. Riscani) | Repair works in kindergarten and gymnasium | 62 177 | 39 485 | 34736 | 22 692 |  |
| 17 | Putinesti (r. Floresti) | Construction of a road portion | 58 311 | 49 564 | 44256 | 8 747 |  |
| 18 | Ramazan (r. Riscani) | Renovation of water supply system | 58 310 | 42 763 | 37526 | 15 547 |  |
| 19 | Sarata Veche (r. Floresti) | Repair works in lyceum | 57 228 | 48 644 | 36063 | 8 584 |  |
| 20 | Slobozia-Cremene (r. Soroca) | Repair works in kindergarten | 55 433 | 47 118 | 35168 | 8 315 |  |
| 21 | Solcani (r. Soroca) | Repair works in gymnasium | 57 906 | 49 220 | 31585 | 8 686 |  |
| 22 | Surii Noi (r. Drochia) | Repair works in kindergarten | 49 889 | 42 404 | 34330 | 7 485 |  |
| 23 | Sverdiac (r. Riscani) | Renovation of water supply system | 58 310 | 49 563 | 35192 | 8 747 |  |
| 24 | Temeleuti (r. Floresti) | Repair works in gymnasium | 57 611 | 48 969 | 30808 | 8 642 |  |
| 25 | Unchitesti (r. Floresti) | Repair works in kindergarten | 50 848 | 39 494 | 9397 | 11 354 |  |
| 26 | Usurei (r. Riscani) | Construction of mainline aqueduct | 31 620 | 26 877 | 18014 | 4 743 |  |
| 27 | Vadeni (r. Soroca) | Repair works in gymnasium | 59 844 | 50 867 | 39485 | 8 977 |  |
| 28 | Varvareuca (r. Floresti) | Repair works in gymnasium | 58 428 | 49 664 | 32875 | 8 764 |  |
| 29 | Volodeni (r. Edinet) | Extension of repair works in kindergarten and gymnasium | 55 667 | 47 317 | 35568 | 8 350 |  |
| 30 | Cenusa (r. Floresti) | Repair works in kindergarten and gymnasium | 54 572 | 46 386 | 33246 | 8 186 |  |
| 31 | Climauti (Donduseni) | Construction of a road portion | 54 358 | 46 204 | 44900 | 8 154 |  |
| 32 | Septelici (r. Soroca) | Construction of a road portion | 54 354 | 46 201 | 43712 | 8 153 |  |
| 33 | Tirgul Vertiujeni (r. Floresti) | Construction of a road portion | 55 035 | 46 780 |  | 8 255 | bidding |
|  | In total: | 32 SPs – implemented, 1 SP – bidding | 1 762 682 | 1 474 383 | 1059224 | 288 299 |  |

Annex 3. Progress of subprojects implementation (“repeatedly come” communities)

3.1. Villages

| # | Community | SP | Estimated budget (EUR) | Estimated KfW FC (EUR) | Disbursed KfW (EUR) | Estimated CC (EUR) | Stage |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Ciutulesti (r. Floresti) | Construction of a portion of aqueduct | 44 407 | 31 085 | 18203 | 13 322 | F i n i s h e d F i n i s h e d F i n i s h e d F i n i s h e d F i n i s h e d F i n i s h e d |
| 2 | Cosauti (r. Soroca) | Repair works in kindergarten | 72 194 | 42 145 | 22544 | 30 049 |  |
| 3 | Gura Cainarului (r. Floresti) | Construction of a portion of aqueduct | 51 894 | 36 325 | 22827 | 15 569 |  |
| 4 | Izvoare (r. Falesti) | Construction of a portion of aqueduct connecting social objects | 55 472 | 38 240 | 24228 | 17 232 |  |
| 5 | Lunga (r. Floresti) | Paving sidewalks | 56 608 | 39 626 | 22415 | 16 982 |  |
| 6 | Recea (r. Riscani) | Paving sidewalks in the centre of the village | 58 336 | 40 835 | 23013 | 17 501 |  |
| 7 | Sturzovca (r. Glodeni) | Repair works in kindergarten nr. 2 | 60 734 | 42 514 | 32738 | 18 220 |  |
| 8 | Tirnova (Donduseni) | Construction of a portion of aqueduct | 45 638 | 31 946 | 19909 | 13 692 |  |
| 9 | Balanul Nou (r. Riscani) | Construction of a portion of aqueduct | 58 843 | 41 190 | 25446 | 17 653 |  |
| 10 | Gura Camencii (r. Floresti) | Repair works in gymnasium | 62 474 | 38 830 | 26937 | 23 644 |  |
| 11 | Hasnasenii Mari (r. Drochia) | Repair of a portion of road | 54 912 | 38 438 | 39321 | 16 474 |  |
| 12 | Navirnet (r. Falesti) | Extension of aqueduct | 30 810 | 21 567 | 12622 | 9 243 |  |
| 13 | Pelinia (r. Drochia) | Interior repair works in kindergarten nr. 1 | 49 266 | 34 486 | 32636 | 14 780 |  |
| 14 | Popestii de Sus (r. Drochia) | Repair works in lyceum | 56 173 | 39 321 | 37177 | 16 852 |  |
| 15 | Prajila (r. Floresti) | Repair works in gymnasium | 59 216 | 38 135 | 23340 | 21 081 |  |
| 16 | Zgurita (r. Drochia) | Repair of some portions of road and sidewalks | 55 140 | 38 598 | 32575 | 16 542 |  |
| 17 | Calarasovca (r. Ocnita) | Repair works in gymnasium | 55 381 | 38 767 | 32632 | 16 614 |  |
| 18 | Grinauti-Moldova (r. Ocnia) | Repair works in gymnasium | 55 414 | 38 790 | 34570 | 16 624 |  |
| 19 | Floresti (r. Floresti) | Construction of a road portion | 189021 | 132315 | 123240 | 56706 |  |
| 20 | Girbova (r.Ocnita) | Renovation of the street lighting network | 35244 | 24671 | 23535 | 10573 |  |
| 21 | Balatina (r. Glodeni) | Repair works in kindergarten nr.2 | 55 480 | 38 836 | 28456 | 16 644 |  |
| 22 | Mihaileni (r. Riscani) | Renovation works at community centre for elders | 113337 | 60604 | 26983 | 52 733 | impl |
|  | In total: | 21 SPs – implemented 1 SP – under implementation | 1 375 994 | 927 264 | 667143 | 448 730 |  |

3.2. Small towns

| # | Community | SP | Estimated budget (EUR) | Estimated KfW FC (EUR) | Disbursed KfW (EUR) | Estimated CC (EUR) | Stage |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Briceni (r. Briceni) | Repair works in the music school | 95 015 | 55 153 | 40011 | 39 862 | F i n i s h e d F i n i s h e d |
| 2 | Drochia (r. Drochia) | Paving sidewalks | 168 566 | 117 996 | 80490 | 50 570 |  |
| 3 | Ocnita (r. Ocnita) | Renovation of the street lighting network | 75 429 | 52 800 | 51908 | 22 629 |  |
| 4 |  | Repair works in the department of Pediatrics and Rehabilitation for children (district hospital) | 49 620 | 34 734 | 33833 | 14 886 |  |
| 5 | Riscani (r. Riscani) | Repair works in gymnasium “Gh. Riscanu” | 87 621 | 61 335 | 63062 | 26 286 |  |
| 6 | Lipcani (r. Briceni) | Renovation of some sectors of the street lighting network | 28 303 | 19 812 | 83214 | 8 491 |  |
| 7 | Lipcani (r. Briceni) | Paving sidewalks | 121 857 | 85 300 |  | 36 557 |  |
|  | In total: | 7SPs – implemented | 626 411 | 427 130 | 352520 | 199 281 |  |

Annex 4. Progress of subprojects implementation in post-conflict region

| # | Community | SP | Estimated budget (EUR) | Estimated KfW FC (EUR) | Disbursed KfW (EUR) | Estimated CC (EUR) | Stage |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Cioburciu (r. Slobozia) | Repair works in the sports school | 48 721 | 41 413 | 30979 | 7 308 | F i n i s h e d F i n i s h e d F i n i s h e d F i n i s h e d F i n i s h e d |
| 2 | Cocieri (r. Dubasari) | Roof replacement at the community cultural centre | 32 433 | 27 568 | 24976 | 4 865 |  |
| 3 | Cocieri (r. Dubasari) | Mounting solar collectors at kindergarten | 4 642 | 3 946 | 2745 | 696 |  |
| 4 | Cosnita (r. Dubasari) | Repair works in kindergarten nr. 2 | 33 080 | 28 118 | 19479 | 4 962 |  |
| 5 | Dorotcaia (r. Dubăsari) | Reconstruction of roof at the kindergarten | 19 961 | 13 973 | 10084 | 5 988 |  |
| 6 | Dorotcaia (r. Dubăsari) | Mounting solar collectors at the kindergarten | 3 966 | 3 371 | 2745 | 595 |  |
| 7 | Molovata Noua (r. Dubasari) | Mounting solar collectors at the kindergarten | 4 774 | 4 058 | 3870 | 716 |  |
| 8 | t.Pervomaisc (r. Slobozia) | Replacement of external doors and windows in the kindergarten | 49 460 | 42 041 | 46679 | 7 419 |  |
| 9 | t.Pervomaisc (r. Slobozia) | Replacement of external doors and windows in the medical centre | 12 687 | 10 784 | 11794 | 1 903 |  |
| 10 | t.Pervomaisc (r. Slobozia) | Reconstruction of roof at the medical centre | 26 986 | 22 938 | 21471 | 4 048 |  |
| 11 | Pirita (r. Dubasari) | Mounting solar collectors at the kindergarten | 2 862 | 2 432 | 2388 | 430 |  |
| 12 | t. Slobozia (r. Slobozia) | Repair works in the kindergarten “Ivushka” | 137 681 | 117 029 | 111642 | 20 652 |  |
| 13 | Colosova (Grigoriopol) | Repair works in kindergarten | 25 215 | 21 433 | 19262 | 3 782 |  |
| 14 | Speia (Grigoriopol) | Repair works in school | 64 572 | 54 887 | 48775 | 9 685 |  |
| 15 | Podoima (r. Camenca) | Repair works in school | 53 943 | 45 851 | 29307 | 8 092 |  |
| 16 | Hlinaia (Grigoriopol) | Repair works in kindergarten | 55 078 | 46 816 | 44329 | 8 262 | F i n i s h e d F i n i s h e d |
| 17 | Maiac (Grigoriopol) | Repair works in school | 54 773 | 46 557 | 39045 | 8 216 |  |
| 18 | Malaiesti (Grigoriopol) | Repair works in school | 54 908 | 46 671 | 38468 | 8 237 |  |
| 19 | Slobozia-Rascov (r. Camenca) | Repair works in the educational centre (school and kindergarten) | 54 076 | 45 964 | 36804 | 8 112 |  |
| 20 | Teiu (Grigoriopol) | Repair works in school | 54 561 | 46 377 | 40025 | 8 184 |  |
| 21 | t. Camenca (r. Camenca) | Repair works in school nr.1 | 79 164 | 67 289 | 56774 | 11 875 |  |
| 22 | Caterinovca (r. Camenca) | Repair works in kindergarten | 54 148 | 46 026 | 42577 | 8 122 |  |
| 23 | Rascov (r. Camenca) | Repair works in the educational centre (school / kindergarten) | 55617 | 47 275 | 44788 | 8 342 |  |
| 24 | t. Dnestrovsc | Repair works in kindergarten nr. 1 | 50857 | 43 228 | 39629 | 7 629 |  |
| 25 | Carmanova (Grigoriopol) | Repair works in school | 64 170 | 54 544 | 137 | 9 626 | impl |
| 26 | Chitcani (r. Slobozia) | Repair works in school nr.2 | 68253 | 55 496 | 37 | 12 757 | impl |
| 27 | t. Camenca (r. Camenca) | Extension of the repair works in school nr. 1 | 125612 | 106770 |  | 18842 | bidding |
|  | In total: | 24 SPs – implemented 2 SPs – under implementation 1 SP - bidding | 1 292 200 | 1 092 855 | 768807 | 199345 |  |

## Annex 5. Subprojects implemented or under implementation

## with KfW and Government of Romania financial contribution

“New” communities

| ## # | Community | SP | Estimated KfW FC (EUR) | Government of Romania FC (EUR) |
| --- | --- | --- | --- | --- |
| 1 | Bulboaca (r. Briceni) | Repair works in kindergarten | 49 462 | 14712 |
| 2 | Mihalaseni (r. Ocnita) | Repair works in educational complex | 59 152 | 20073 |
| 3 | Ocolina (r. Soroca) | Repair works in kindergarten | 42 038 | 9267 |
| 4 | Petreni (r.Drochia) | Repair works in kindergarten | 21 610 | 32172 |
| 5 | Pirjota (r. Riscani) | Repair works in kindergarten | 39 485 | 4990 |
| 6 | Volodeni (r. Edinet) | Extension of repair works in kindergarten | 47 317 | 23425 |
| Total |  |  | 259064 | 104639 |

“Repeatedly come” communities

| # | Community | SP | Estimated KfW FC (EUR) | Government of Romania FC (EUR) |
| --- | --- | --- | --- | --- |
| 1 | Balatina (r. Glodeni) | Repair works in kindergarten nr. 2 | 38 836 | 21261 |
| Total |  |  | 38 836 | 21261 |

## Annex 6. Selective Project performance results

| # | Activity | Cumulatively per Grant | Reference period (01.01-30.06.2015) |
| --- | --- | --- | --- |
| 1. | Public involvement in community development |  |  |
|  | Identification of community priority needs: |  |  |
|  | Focus groups | 516 | 0 |
|  | Community general/representatives meetings, referendums and open local sessions | 134 | 0 |
|  | People involved | 68760 | 0 |
|  | Training of community leaders and beneficiaries | 2022 | 60 |
| 2. | Procurement activity |  |  |
|  | Tenders to select construction companies and local supervisors | 123 | 8 |
|  | Bidders | 449 | 20 |
|  | Concluded contracts | 123 | 6 |
| 3. | Financial activity (EUR mln) |  |  |
|  | Committed total | 5,7 | 0,047 |
|  | FC disbursed, including | 3,18 | 0,3 |
|  | “new” communities | 1.059.224 |  |
|  | “repeatedly come” communities (villages and small towns) | 1.019.663 |  |
|  | Post-conflict region | 768.807 |  |
|  | passive house | 25.793 |  |
|  | MSIF admin cost | 306.638 |  |
| 4. | Community contribution collected (EUR mln) | 1,025 |  |
|  | CC disbursed | 0,86 | 0,18 |
| 5. | Implementation of infrastructure subprojects |  |  |
|  | Implemented subprojects | 84 | 13 |
|  | Temporary workplaces | 2178 | 118 |
| 6. | Beneficiaries of a better access to the improved infrastructure services | 62586 | 16120 |